## Slide 1
PROPERTY SECURITY
Action Plan & Next Steps
7 March 2026 | Stream 1

## Slide 2
2
Overview & Status
Stream 1 — Property Security
Deadline: May 2026 (all actions)
Status: Content largely produced; governance, distribution, and delivery are the critical gaps
5 priorities identified across governance, content, distribution, delivery, and lobbying
Key blocker: No action in this stream has a named lead

## Slide 3
3
At a Glance
5
Priorities
Identified
MAY '26
Target
Deadline
7
Key
Milestones

## Slide 4
4
Priority 1: Assign Leads
Target: by 14 March 2026
This is the single blocker for everything else

## Slide 5
5
Priority 1: Assign Leads
Task | Detail | Owner | Target Date
1.1 | Identify and confirm a Stream Lead for Property Security — chairs the working group, accountable for May 2026 deadline | IAG Stewardship Group | 14 Mar 2026
1.2 | Assign an Action Lead for each of the 3 actions (can be same person for Actions 1 & 2; Action 3 needs policy/lobbying experience) | Stream Lead | 14 Mar 2026
1.3 | Convene a kickoff meeting of the working group to review existing materials and agree the delivery plan | Stream Lead | 21 Mar 2026
Likely organisations to draw leads from: MCB (authored briefing paper and all current materials), MEND (mosque security training expertise), MCF (trustee networks).

## Slide 6
6
Priority 2: Finalise Content
Target: by 28 March 2026
Small content gaps that can be closed quickly once leads are in place

## Slide 7
7
Priority 2: Finalise Outstanding Content
Task | Action | Detail | Owner | Target
2.1 | Action 3 | Finalise PSMS form contact details — confirm submission email and postal address | Action 3 Lead | 14 Mar 2026
2.2 | Action 2 | Create a 1-page Martyn's Law summary handout — key facts in printable format for attendees | Action 2 Lead | 28 Mar 2026
2.3 | Action 1 | Write a cover letter / launch communication introducing the Security Preparedness Framework | Action 1 Lead | 28 Mar 2026
2.4 | Action 1 | Schools & Madrassah Annex — added as Appendix F in v1.4 of the Physical Security Guide | Done | Complete
2.5 | Action 1 | Add guidance for commercial premises — a short annex addressing halal shops, restaurants, and other Muslim-associated businesses | Action 1 Lead | 18 Apr 2026

## Slide 8
8
Priority 3: Distribution Plan
Target: by 4 April 2026
A single distribution plan can serve all three actions

## Slide 9
9
Priority 3: Distribution Plan
Task | Detail | Owner | Target
3.1 | Map distribution channels — MCB affiliates, MEND regional networks, mosque umbrella bodies, councils of mosques, social media, Friday khutbah announcement templates | Stream Lead | 28 Mar 2026
3.2 | Create a distribution pack — bundle all Action 1 docs + Martyn's Law handout + PSMS evidence form into a single downloadable pack with cover letter | Action 1 Lead | 4 Apr 2026
3.3 | Set up a webpage or shared drive link where mosques can access all materials — a single URL for email, WhatsApp, and social media | Stream Lead | 4 Apr 2026
3.4 | Draft email/WhatsApp announcement for distribution to mosque contacts introducing the pack and linking to the webpage | Stream Lead | 4 Apr 2026
3.5 | Coordinate with Stream 2 (Community Empowerment) — if a digital platform is being developed, ensure Property Security materials are included from launch | Stream Lead | Ongoing

## Slide 10
10
Priority 4: Martyn's Law Webinar
Target: first session by 18 April 2026
The webinar content is ready — it needs a delivery mechanism

## Slide 11
11
Priority 4: Webinar Delivery
Task | Detail | Owner | Target
4.1 | Decide platform — Zoom, Teams, or YouTube Live; consider recording for on-demand access | Action 2 Lead | 21 Mar 2026
4.2 | Schedule at least 2 live webinar sessions before May 2026 — one weekday evening, one weekend; consider a Ramadan-timed session | Action 2 Lead | 28 Mar 2026
4.3 | Set up registration — Google Form or Eventbrite to capture attendee details and mosque names for reach tracking | Action 2 Lead | 4 Apr 2026
4.4 | Deliver first webinar | Action 2 Lead | 18 Apr 2026
4.5 | Record and publish — make available via the distribution webpage (task 3.3) for mosques that cannot attend live | Action 2 Lead | 25 Apr 2026
4.6 | Deliver second webinar | Action 2 Lead | 2 May 2026

## Slide 12
12
Priority 5: PSMS Lobbying Strategy
Target: by 2 May 2026
The evidence form gathers data — a strategy is needed to turn it into policy impact

## Slide 13
13
Priority 5: PSMS Lobbying Strategy
Task | Detail | Owner | Target
5.1 | Distribute the PSMS evidence form via Priority 3 channels — aim for responses from at least 50 mosques | Action 3 Lead | 11 Apr 2026
5.2 | Set a response deadline — allow 3-4 weeks for mosques to complete and return the form | Action 3 Lead | 11 Apr 2026
5.3 | Identify lobbying targets — relevant MPs (Home Affairs Committee), constituency MPs, Home Office officials, APPG on British Muslims | Action 3 Lead | 18 Apr 2026
5.4 | Synthesise evidence — analyse returned forms, produce summary report with anonymised case studies and aggregate statistics | Action 3 Lead | 2 May 2026
5.5 | Draft a policy submission building on the existing MCB Briefing Paper, updated with fresh evidence from responses | Action 3 Lead | 16 May 2026
5.6 | Schedule meetings with target MPs/officials to present findings | Action 3 Lead | May-Jun 2026

## Slide 14
14
Important: Lobbying Timeline
The May 2026 deadline for Action 3 is likely too tight for full lobbying impact.
Recommended reframing:
Evidence collection and synthesis complete by May 2026
Active lobbying June — October 2026
Key advocacy moments:
  Southport anniversary (July 2026)
  Peacehaven anniversary (October 2026)

## Slide 15
15
Monitoring Milestones
Milestone | Target Date | How We'll Know It's Done
Leads assigned | 14 Mar 2026 | Named individuals confirmed in README
Kickoff meeting held | 21 Mar 2026 | Meeting notes circulated
Content finalised | 28 Mar 2026 | All documents at v1.0+, PSMS form contact details confirmed
Distribution pack live | 4 Apr 2026 | URL accessible and shared
First webinar delivered | 18 Apr 2026 | Recording available, attendance logged
PSMS responses collected | 2 May 2026 | 50+ responses received
Evidence synthesis complete | 16 May 2026 | Summary report produced

## Slide 16
16
Risks & Mitigations
Risk | Mitigation
No leads assigned — everything stalls | Escalate to IAG Stewardship Group immediately; this is the #1 blocker
Low response rate on PSMS form — insufficient evidence base | Use multiple channels, follow up personally with known mosques, offer phone-based completion
Webinar attendance is low — mosques don't engage | Record for on-demand viewing; promote via Friday khutbah templates; partner with MEND's existing training sessions
May 2026 deadline is missed — content ready but not distributed | Accept phased delivery: content done by May, distribution and lobbying through summer/autumn 2026
Commercial premises gap — shops/restaurants feel excluded | Produce a targeted short guide; engage with halal trade bodies if they exist

## Slide 17
Thank You
Property Security — Stream 1
www.mcb.org.uk